## Dashboard
ASO Phase 11 Workbook — UAT, Production Deployment, and Hypercare
Customer-ready enterprise/MVP tracking workbook for Agentic Sales Orchestrator.
Current phase | Phase 11 | Phase Control Dashboard
Objective | Validate business readiness, deploy managed solutions, run cutover, monitor hypercare, and transition to operations. | Total tasks | 14
Primary solution/component | All ASO solutions and operations model | Done | 0
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — go-live checklist, production runbooks, target operating model and governance | In progress | 0
Enterprise target | UAT signoff, production readiness, managed solution deployment, cutover plan, monitoring live, runbooks approved, governance board active, and hypercare completed. | Blocked | 0
MVP/trial adaptation | For demo/MVP, document that production deployment is not executed and use the workbook as a readiness checklist for future production upgrade. | Completion % | 0%
Non-negotiable | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Open risks/issues | 3
|  | Open production gaps | 3
|  | Validation passed | 0
|  | Phase Gate Criteria | Status | Evidence / notes
|  | Prerequisites confirmed | Not Started
|  | Build tracker complete or deferred with approval | Not Started
|  | Validation checklist passed | Not Started
|  | Risks/issues assessed | Not Started
|  | Production gaps logged | Not Started
|  | Solution/export evidence recorded | Not Started
|  | Architecture boundaries preserved | Not Started

## Phase Charter
Phase 11 Charter
Scope, assumptions, boundaries, and operating model for this phase.
Field | Value
Phase | Phase 11 — UAT, Production Deployment, and Hypercare
Objective | Validate business readiness, deploy managed solutions, run cutover, monitor hypercare, and transition to operations.
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — go-live checklist, production runbooks, target operating model and governance
Primary solution/component | All ASO solutions and operations model
Enterprise target | UAT signoff, production readiness, managed solution deployment, cutover plan, monitoring live, runbooks approved, governance board active, and hypercare completed.
MVP/trial-friendly implementation | For demo/MVP, document that production deployment is not executed and use the workbook as a readiness checklist for future production upgrade.
What to simulate if blocked | Use mocks/placeholders/manual validation only where product trial or licensing limits block the real enterprise component. Record every shortcut as MVP-only.
What to skip for now | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete.
Architecture boundary | Dataverse is operational truth; Customer Insights handles outbound lifecycle communications; Power Automate executes deterministically; Foundry orchestrates; SAP only through APIM + Azure Functions; HubSpot is ingress only and last.

## Build Tracker
Phase 11 Build Tracker
Track every build/configuration item through owner, status, evidence and validation.
ID | Work item | Stream | Implementation instruction | Expected outcome | Owner role | Status | Priority | Start date | Target date | Completed date | Evidence / link | Validation result | Notes
11.1 | Prepare UAT scope and scripts | UAT | Lead, opportunity, CIJ, SAP, agent, Foundry, flow, HubSpot scenarios | UAT pack ready | Project Manager | Not Started | High
11.2 | Confirm go-live checklist | Readiness | Environment, solutions, connections, variables, schema, forms, roles, CIJ, SAP, agents, Foundry, flows, HubSpot, monitoring | Checklist reviewed | Solution Architect | Not Started | High
11.3 | Validate security roles and FLS | Security | Least privilege roles and field-level protections | Security signoff | Security Lead | Not Started | High
11.4 | Validate compliance and consent | Compliance | Customer Insights profiles, topics, unsubscribe/preference center | Compliance signoff | Marketing/Compliance | Not Started | High
11.5 | Validate managed solution deployment | ALM | Managed imports through promotion path | Deployment evidence captured | Release Manager | Not Started | High
11.6 | Run production cutover rehearsal | Cutover | Sequence, owners, rollback, comms, freeze window | Rehearsal complete | Release Manager | Not Started | High
11.7 | Prepare rollback plan | Release | Solution rollback/backout approach and data handling | Rollback approved | Release Manager | Not Started | High
11.8 | Confirm monitoring and alerts live | Operations | App Insights, dashboards, alerts, runbooks | Ops signoff | Ops Lead | Not Started | High
11.9 | Train support and business users | Change | Sellers, managers, ops reviewers, CI operators, integration operators | Training complete | Change Manager | Not Started | Medium
11.10 | Execute production deployment | Deployment | Only after approval; managed solutions and configs | Deployment completed or MVP-only gap logged | Release Manager | Not Started | High
11.11 | Run smoke tests | Testing | Core flows, lead, opportunity, CIJ, SAP, dashboards, HubSpot | Smoke tests passed | Tester | Not Started | High
11.12 | Start hypercare | Operations | Daily monitoring, defect triage, KPI review | Hypercare active | Ops Lead | Not Started | High
11.13 | Complete hypercare exit | Operations | Open defects acceptable, SLAs met, handover complete | Exit signed off | Project Sponsor | Not Started | High
11.14 | Transition to target operating model | Governance | Governance board, change process, runbook ownership | BAU handover complete | Ops Lead | Not Started | Medium

## Runbook
Phase 11 Click-by-Click Runbook
Operational build notes for step-by-step execution. Keep evidence and blockers current.
Step | Click path / action | Exact name or value | Configuration notes | Expected UI result | Common mistake to avoid | Status | Evidence
11.1 | Lead, opportunity, CIJ, SAP, agent, Foundry, flow, HubSpot scenarios |  | UAT pack ready | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.2 | Environment, solutions, connections, variables, schema, forms, roles, CIJ, SAP, agents, Foundry, flows, HubSpot, monitoring |  | Checklist reviewed | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.3 | Least privilege roles and field-level protections |  | Security signoff | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.4 | Customer Insights profiles, topics, unsubscribe/preference center |  | Compliance signoff | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.5 | Managed imports through promotion path |  | Deployment evidence captured | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.6 | Sequence, owners, rollback, comms, freeze window |  | Rehearsal complete | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.7 | Solution rollback/backout approach and data handling |  | Rollback approved | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.8 | App Insights, dashboards, alerts, runbooks |  | Ops signoff | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.9 | Sellers, managers, ops reviewers, CI operators, integration operators |  | Training complete | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.10 | Only after approval; managed solutions and configs |  | Deployment completed or MVP-only gap logged | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.11 | Core flows, lead, opportunity, CIJ, SAP, dashboards, HubSpot |  | Smoke tests passed | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.12 | Daily monitoring, defect triage, KPI review |  | Hypercare active | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.13 | Open defects acceptable, SLAs met, handover complete |  | Exit signed off | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started
11.14 | Governance board, change process, runbook ownership |  | BAU handover complete | Visible/configured in the correct solution/component | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Not Started

## Config Register
Phase 11 Configuration Register
Names, values, IDs, owners and environment-specific configuration.
Type | Name / schema | Purpose / value | Required level | MVP note | Owner | Status | Environment | Actual value / ID | Evidence / link
Promotion Path | Dev → SIT → UAT → Pre-Prod → Prod | Enterprise deployment path | Required for production | MVP may not have all environments |  | Not Started | DEV
Solution Mode | Managed in higher environments | ALM rule | Required | No unmanaged production customizations |  | Not Started | DEV
Hypercare Cadence | Daily | Initial support rhythm | Recommended | Adjust after stabilization |  | Not Started | DEV
Governance Board | Weekly operations / monthly architecture / quarterly strategy | Operating model | Recommended | Confirm members |  | Not Started | DEV

## Validation Checklist
Phase 11 Validation Checklist
Gate checks that must pass before the next major phase.
ID | Validation item | Expected evidence | Owner | Criticality | Passed? | Evidence / link | Notes
VAL-11.1 | UAT scripts and results are approved | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-11.2 | Go-live checklist is complete | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-11.3 | Managed solution deployment is tested | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-11.4 | Security and compliance signoff are complete | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-11.5 | Monitoring and runbooks are live | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-11.6 | Rollback plan is approved | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-11.7 | Smoke tests pass | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-11.8 | Hypercare entry and exit criteria are defined | Screenshot, record URL, export file, test result, or decision log entry |  | High | No

## Decision Log
Phase 11 Decision Log
Architecture, MVP shortcut, security, ALM, data, integration and product decisions.
Decision ID | Date | Decision area | Decision | Options considered | Rationale | Owner | Status | Impacted phase/component | Follow-up action
DEC-11.001 | 46161 | Scope | Use this workbook as the control file for Phase 11. | Use ad hoc notes; use one master tracker; use phase workbook | Separate phase workbook gives clear gate control and upgrade path. | Solution Architect | Approved | Phase 11
DEC-11.002 | 46161 | MVP adaptation | All demo shortcuts must be recorded in Production Gap Log. | Ignore shortcuts; document later; record immediately | Prevents MVP shortcuts becoming hidden production risks. | Project Manager | Approved | Phase 11

## Risk & Issue Log
Phase 11 Risk & Issue Log
Track delivery risks, blockers, mitigations, and resolution evidence.
ID | Type | Area | Risk / issue | Impact | Probability | Mitigation / action | Status | Owner | Due date | Evidence / notes
RISK-11.001 | Risk | MVP constraints | Trial/free-tier limitations may block enterprise components. | May require mocks/manual validation | Medium | Document blocker and production gap; preserve target architecture boundary. | Open
RISK-11.002 | Risk | ALM | Single DEV environment can hide promotion issues. | Production upgrade risk | Medium | Export solution backups; document future environment runway. | Open
RISK-11.003 | Risk | Architecture boundary | Do not claim production readiness if environments, security, monitoring, integrations, compliance, and UAT are not complete. | Supportability and governance risk | Low | Use validation checklist and phase gate before progressing. | Open

## Production Gap Log
Phase 11 Production Gap Log
Every MVP simplification must have a production risk and upgrade path.
Area | MVP decision | Production gap | Risk / limitation | Future production action | Owner | Status | Target phase/date | Decision reference
MVP/demo | Do not deploy to production | No production readiness proof | MVP-only limitation; assess before production | Use this workbook as production upgrade checklist |  | Open
Environment runway | May lack SIT/UAT/PREPROD/PROD | Cannot perform true promotion validation | MVP-only limitation; assess before production | Create production ALM runway |  | Open
Operations | Manual hypercare in MVP | No full ITSM integration | MVP-only limitation; assess before production | Integrate with service management before production |  | Open

## Security & Controls
Phase 11 Security & Controls
Security, compliance, data, integration, AI and ALM control checks.
Control area | Control requirement | Applies in this phase? | MVP implementation | Production expectation | Owner | Status | Evidence / notes
ALM | All changes are solution-aware; no default solution build | Yes | Use named ASO solution(s) | Managed solution promotion with pipeline |  | Not Started
Security | Least privilege and admin access restrictions | Yes | Document roles; limit admin access | RBAC/FLS fully enforced |  | Not Started
Data integrity | External IDs, keys, dedupe where applicable | Conditional | Create or document controls | Automated enforcement |  | Not Started
AI governance | AI output advisory until validated by governed orchestration | Conditional | Use review fields and decision log | Foundry policy/evals |  | Not Started
Communication governance | Customer Insights is the only lifecycle outbound channel | Conditional | Do not send outside CIJ | Compliance profile, consent, audit |  | Not Started
SAP boundary | SAP only through APIM + Azure Functions | Conditional | Mock or contract-only where unavailable | APIM/JWT/idempotency/telemetry |  | Not Started
Secrets | No secrets in workbook, flows, code or prompts | Yes | Use placeholders | Key Vault and managed identity |  | Not Started
Observability | Correlation IDs and run logging | Conditional | Use logs/registers | App Insights + Dataverse dashboards |  | Not Started

## ALM & Release
Phase 11 ALM & Release Register
Track solution exports, versioning, deployment evidence and rollback notes.
ID | Solution/component | Version | Change summary | Export/deploy type | Environment | Date | Owner | File/link | Validation status | Rollback notes
ALM-11.001 | All ASO solutions and operations model | 0.1.0 | Initial Phase 11 setup | Manual export backup | DEV |  |  |  | Not Started

## Test Data
Phase 11 Test Data Register
Synthetic records and test users used during MVP/demo validation.
ID | Record type | Record name | Purpose | Created in environment | Owner | Data classification | Cleanup needed? | Status | Notes
TD-11.001 | Lead/Opportunity/Account/Contact or component-specific test item | ASO MVP TEST - example | Phase validation | DEV |  | Synthetic/demo only | Yes | Not Started | Do not use real customer data

## Go Live Checklist
Phase 11 — Go Live Checklist
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Checklist item | Required? | Owner | Status | Evidence | Notes
Dev/SIT/UAT/Prod environments created or MVP gap accepted | Yes |  | Not Started
Solutions created and publisher confirmed | Yes |  | Not Started
Connection references configured | Yes |  | Not Started
Environment variables configured | Yes |  | Not Started
Dataverse schema/forms/views/security complete | Yes |  | Not Started
Customer Insights installed and compliance assets approved | Yes |  | Not Started
SAP/APIM/Functions validated | Yes |  | Not Started
Sales agents configured and tested | Yes |  | Not Started
Foundry orchestrator deployed and evaluated | Yes |  | Not Started
Power Automate flows tested | Yes |  | Not Started
HubSpot sync tested last | Yes |  | Not Started
Monitoring and alerts live | Yes |  | Not Started
Runbooks approved | Yes |  | Not Started
UAT signed off | Yes |  | Not Started
Production cutover approved | Yes |  | Not Started

## Cutover Plan
Phase 11 — Cutover Plan
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Sequence | Activity | Owner | Planned start | Planned finish | Dependency | Rollback step | Status | Notes
1 | Freeze changes | Release Manager |  |  | Go-live approval | Unfreeze / rollback communication | Not Started
2 | Import managed solutions | Release Manager |  |  | Package approved | Restore previous solution version | Not Started

## Hypercare Log
Phase 11 — Hypercare Log
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Date | Issue/observation | Severity | Owner | Action | Status | Resolution | Notes
|  | Medium |  |  | Open

## Source References
Phase 11 Source References
Source files and guide sections used to populate this workbook.
Source | Relevant section / use | Notes
MAIN_Agentic Sales Orchestrator - Build Guide.md | Delivery phases, target architecture, product boundaries, naming standards, phase runbook content | Primary enterprise guide for all phases
ASO_Phase2_Dataverse_Schema_Sales_Form_MVP_Guidance.md | Phase 2 MVP guidance, data dictionary/security/gap tracking and Dataverse schema runbook | Primary detailed guide for Phase 2 workbook
Pasted text.txt | MVP adaptation rules, answer structure, documentation expectations, architecture boundary rules | Used to align workbook controls and phase-gate style
D365_Success_by_Design.docx | General delivery assurance context | Referenced as general programme quality context where relevant