## Dashboard
ASO Phase 3 Workbook — Customer Insights - Journeys Communication Plane
Customer-ready enterprise/MVP tracking workbook for Agentic Sales Orchestrator.
Current phase | Phase 3 | Phase Control Dashboard
Objective | Prepare the governed outbound communication layer with compliance profile, triggers, segments, email assets, journeys, and writeback requirements. | Total tasks | 17
Primary solution/component | ASO.Journeys / ASO.Core / ASO.Automation | Done | 0
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — Phase 3 / Customer Insights sections | In progress | 0
Enterprise target | Customer Insights - Journeys is installed, sending domain authenticated, compliance profiles and topics published, triggers/segments/email assets/journeys created, and writeback rules defined. | Blocked | 0
MVP/trial adaptation | If CIJ trial capability is limited, configure what is available, simulate journey entry/writeback in Dataverse, and document domain/compliance/send limitations. | Completion % | 0%
Non-negotiable | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Open risks/issues | 3
|  | Open production gaps | 3
|  | Validation passed | 0
|  | Phase Gate Criteria | Status | Evidence / notes
|  | Prerequisites confirmed | Not Started
|  | Build tracker complete or deferred with approval | Not Started
|  | Validation checklist passed | Not Started
|  | Risks/issues assessed | Not Started
|  | Production gaps logged | Not Started
|  | Solution/export evidence recorded | Not Started
|  | Architecture boundaries preserved | Not Started

## Phase Charter
Phase 3 Charter
Scope, assumptions, boundaries, and operating model for this phase.
Field | Value
Phase | Phase 3 — Customer Insights - Journeys Communication Plane
Objective | Prepare the governed outbound communication layer with compliance profile, triggers, segments, email assets, journeys, and writeback requirements.
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — Phase 3 / Customer Insights sections
Primary solution/component | ASO.Journeys / ASO.Core / ASO.Automation
Enterprise target | Customer Insights - Journeys is installed, sending domain authenticated, compliance profiles and topics published, triggers/segments/email assets/journeys created, and writeback rules defined.
MVP/trial-friendly implementation | If CIJ trial capability is limited, configure what is available, simulate journey entry/writeback in Dataverse, and document domain/compliance/send limitations.
What to simulate if blocked | Use mocks/placeholders/manual validation only where product trial or licensing limits block the real enterprise component. Record every shortcut as MVP-only.
What to skip for now | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry.
Architecture boundary | Dataverse is operational truth; Customer Insights handles outbound lifecycle communications; Power Automate executes deterministically; Foundry orchestrates; SAP only through APIM + Azure Functions; HubSpot is ingress only and last.

## Build Tracker
Phase 3 Build Tracker
Track every build/configuration item through owner, status, evidence and validation.
ID | Work item | Stream | Implementation instruction | Expected outcome | Owner role | Status | Priority | Start date | Target date | Completed date | Evidence / link | Validation result | Notes
3.1 | Confirm Customer Insights - Journeys installation | Prerequisite | Check app installed in DEV | App available or limitation logged | Admin | Not Started | High
3.2 | Configure sending domain | Compliance | Authenticate sending domain or document trial limitation | Domain verified or MVP gap logged | Marketing/CI Operator | Not Started | High
3.3 | Create compliance profile | Compliance | Name Global Commercial or region equivalent | Profile published/tested | Marketing/CI Operator | Not Started | High
3.4 | Create purpose and topics | Consent | Sales Lifecycle purpose; Lead, Qualified Lead, Opportunity, Quote Proposal, Order, Onboarding, Retention, Expansion topics | Topics published | Marketing/CI Operator | Not Started | High
3.5 | Create Dataverse/custom triggers | Triggers | ASO Lead Nurture Requested, Qualified Lead Follow Up, Opportunity Progression, Quote Proposal, Order Confirmation, Onboarding | Triggers ready/published | Marketing/CI Operator | Not Started | High
3.6 | Create Lead - Nurture Ready segment | Segments | Lifecycle=Lead; Communication State=Eligible; Consent=OptedIn; Not Active | Segment published | Marketing/CI Operator | Not Started | Medium
3.7 | Create Qualified Lead segment | Segments | QualifiedLead ready segment | Segment published | Marketing/CI Operator | Not Started | Medium
3.8 | Create Opportunity Proposal segment | Segments | Opportunity/QuoteProposal eligible contacts | Segment published | Marketing/CI Operator | Not Started | Medium
3.9 | Create order/onboarding/retention/expansion segments | Segments | Lifecycle segments | Segments published | Marketing/CI Operator | Not Started | Medium
3.10 | Create governed email assets | Email Assets | Lead nurture, QL follow-up, opportunity, quote, order, onboarding, retention, expansion | Emails approved/test-ready | Marketing/CI Operator | Not Started | Medium
3.11 | Create Lead Nurture journey | Journeys | Segment or trigger entry, email, wait, branches, custom action | Journey tested/published if allowed | Marketing/CI Operator | Not Started | High
3.12 | Create Qualified Lead journey | Journeys | Follow-up and task signal | Journey tested/published if allowed | Marketing/CI Operator | Not Started | Medium
3.13 | Create Opportunity Progression journey | Journeys | Stage-specific engagement | Journey tested/published if allowed | Marketing/CI Operator | Not Started | Medium
3.14 | Create Quote Proposal journey | Journeys | Proposal communication and engagement tracking | Journey tested/published if allowed | Marketing/CI Operator | Not Started | Medium
3.15 | Create Order/Onboarding journey | Journeys | Only after SAP response validated later | Journey draft/test only | Marketing/CI Operator | Not Started | Medium
3.16 | Define writeback requirements | Writeback | Communication State, Journey Status, Journey ID/Name, Last Interaction, Consent, Hold Reason, Ledger rows | Writeback mapping registered | Solution Architect | Not Started | High
3.17 | Phase gate: CIJ boundary validated | Gate | Confirm only CIJ handles outbound lifecycle communications | Gate signed off | Solution Architect | Not Started | High

## Runbook
Phase 3 Click-by-Click Runbook
Operational build notes for step-by-step execution. Keep evidence and blockers current.
Step | Click path / action | Exact name or value | Configuration notes | Expected UI result | Common mistake to avoid | Status | Evidence
3.1 | Check app installed in DEV |  | App available or limitation logged | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.2 | Authenticate sending domain or document trial limitation |  | Domain verified or MVP gap logged | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.3 | Name Global Commercial or region equivalent |  | Profile published/tested | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.4 | Sales Lifecycle purpose; Lead, Qualified Lead, Opportunity, Quote Proposal, Order, Onboarding, Retention, Expansion topics |  | Topics published | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.5 | ASO Lead Nurture Requested, Qualified Lead Follow Up, Opportunity Progression, Quote Proposal, Order Confirmation, Onboarding |  | Triggers ready/published | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.6 | Lifecycle=Lead; Communication State=Eligible; Consent=OptedIn; Not Active |  | Segment published | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.7 | QualifiedLead ready segment |  | Segment published | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.8 | Opportunity/QuoteProposal eligible contacts |  | Segment published | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.9 | Lifecycle segments |  | Segments published | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.10 | Lead nurture, QL follow-up, opportunity, quote, order, onboarding, retention, expansion |  | Emails approved/test-ready | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.11 | Segment or trigger entry, email, wait, branches, custom action |  | Journey tested/published if allowed | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.12 | Follow-up and task signal |  | Journey tested/published if allowed | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.13 | Stage-specific engagement |  | Journey tested/published if allowed | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.14 | Proposal communication and engagement tracking |  | Journey tested/published if allowed | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.15 | Only after SAP response validated later |  | Journey draft/test only | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.16 | Communication State, Journey Status, Journey ID/Name, Last Interaction, Consent, Hold Reason, Ledger rows |  | Writeback mapping registered | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started
3.17 | Confirm only CIJ handles outbound lifecycle communications |  | Gate signed off | Visible/configured in the correct solution/component | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Not Started

## Config Register
Phase 3 Configuration Register
Names, values, IDs, owners and environment-specific configuration.
Type | Name / schema | Purpose / value | Required level | MVP note | Owner | Status | Environment | Actual value / ID | Evidence / link
Compliance Profile | Global Commercial | Default commercial compliance profile | Required | Use tenant/regional equivalent if needed |  | Not Started | DEV
Purpose | Sales Lifecycle | Lifecycle communication consent purpose | Required | Attach to email/journeys |  | Not Started | DEV
Trigger | ASO Lead Nurture Requested | Lead lifecycle journey trigger | Recommended | Use Dataverse/custom trigger per tenant |  | Not Started | DEV
Segment | Lead - Nurture Ready | Lead nurture eligible records | Required | Based on normalized Dataverse fields |  | Not Started | DEV
Email | EML - Lead Nurture - Initial | Initial lead nurture asset | Recommended | Must include unsubscribe/preferences |  | Not Started | DEV
Journey | JRNY - ASO - Lead Nurture - v1 | Lead nurture journey | Recommended | Publish only after compliance validation |  | Not Started | DEV

## Validation Checklist
Phase 3 Validation Checklist
Gate checks that must pass before the next major phase.
ID | Validation item | Expected evidence | Owner | Criticality | Passed? | Evidence / link | Notes
VAL-3.1 | Customer Insights - Journeys app is available or trial limitation logged | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-3.2 | Compliance profile and topics are published or blockers logged | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-3.3 | No lifecycle communication is sent outside Customer Insights | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-3.4 | Segments use normalized Dataverse fields from Phase 2 | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-3.5 | Email assets include compliance/unsubscribe requirements | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-3.6 | Journey names and IDs are recorded | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-3.7 | Writeback mapping to Dataverse fields is documented | Screenshot, record URL, export file, test result, or decision log entry |  | High | No

## Decision Log
Phase 3 Decision Log
Architecture, MVP shortcut, security, ALM, data, integration and product decisions.
Decision ID | Date | Decision area | Decision | Options considered | Rationale | Owner | Status | Impacted phase/component | Follow-up action
DEC-3.001 | 46161 | Scope | Use this workbook as the control file for Phase 3. | Use ad hoc notes; use one master tracker; use phase workbook | Separate phase workbook gives clear gate control and upgrade path. | Solution Architect | Approved | Phase 3
DEC-3.002 | 46161 | MVP adaptation | All demo shortcuts must be recorded in Production Gap Log. | Ignore shortcuts; document later; record immediately | Prevents MVP shortcuts becoming hidden production risks. | Project Manager | Approved | Phase 3

## Risk & Issue Log
Phase 3 Risk & Issue Log
Track delivery risks, blockers, mitigations, and resolution evidence.
ID | Type | Area | Risk / issue | Impact | Probability | Mitigation / action | Status | Owner | Due date | Evidence / notes
RISK-3.001 | Risk | MVP constraints | Trial/free-tier limitations may block enterprise components. | May require mocks/manual validation | Medium | Document blocker and production gap; preserve target architecture boundary. | Open
RISK-3.002 | Risk | ALM | Single DEV environment can hide promotion issues. | Production upgrade risk | Medium | Export solution backups; document future environment runway. | Open
RISK-3.003 | Risk | Architecture boundary | Do not send customer lifecycle communications through Outlook, Power Automate, Sales agents, or Foundry. | Supportability and governance risk | Low | Use validation checklist and phase gate before progressing. | Open

## Production Gap Log
Phase 3 Production Gap Log
Every MVP simplification must have a production risk and upgrade path.
Area | MVP decision | Production gap | Risk / limitation | Future production action | Owner | Status | Target phase/date | Decision reference
Sending domain | Use trial/default or no-send mode | No production domain authentication | MVP-only limitation; assess before production | Authenticate production domain before live send |  | Open
Compliance profile | Use available profile settings | May not match regional/legal operating model | MVP-only limitation; assess before production | Complete legal/compliance review |  | Open
Journey writeback | Document mapping now | Automated sync may wait for Phase 7 | MVP-only limitation; assess before production | Implement Power Automate sync flows |  | Open

## Security & Controls
Phase 3 Security & Controls
Security, compliance, data, integration, AI and ALM control checks.
Control area | Control requirement | Applies in this phase? | MVP implementation | Production expectation | Owner | Status | Evidence / notes
ALM | All changes are solution-aware; no default solution build | Yes | Use named ASO solution(s) | Managed solution promotion with pipeline |  | Not Started
Security | Least privilege and admin access restrictions | Yes | Document roles; limit admin access | RBAC/FLS fully enforced |  | Not Started
Data integrity | External IDs, keys, dedupe where applicable | Conditional | Create or document controls | Automated enforcement |  | Not Started
AI governance | AI output advisory until validated by governed orchestration | Conditional | Use review fields and decision log | Foundry policy/evals |  | Not Started
Communication governance | Customer Insights is the only lifecycle outbound channel | Conditional | Do not send outside CIJ | Compliance profile, consent, audit |  | Not Started
SAP boundary | SAP only through APIM + Azure Functions | Conditional | Mock or contract-only where unavailable | APIM/JWT/idempotency/telemetry |  | Not Started
Secrets | No secrets in workbook, flows, code or prompts | Yes | Use placeholders | Key Vault and managed identity |  | Not Started
Observability | Correlation IDs and run logging | Conditional | Use logs/registers | App Insights + Dataverse dashboards |  | Not Started

## ALM & Release
Phase 3 ALM & Release Register
Track solution exports, versioning, deployment evidence and rollback notes.
ID | Solution/component | Version | Change summary | Export/deploy type | Environment | Date | Owner | File/link | Validation status | Rollback notes
ALM-3.001 | ASO.Journeys / ASO.Core / ASO.Automation | 0.1.0 | Initial Phase 3 setup | Manual export backup | DEV |  |  |  | Not Started

## Test Data
Phase 3 Test Data Register
Synthetic records and test users used during MVP/demo validation.
ID | Record type | Record name | Purpose | Created in environment | Owner | Data classification | Cleanup needed? | Status | Notes
TD-3.001 | Lead/Opportunity/Account/Contact or component-specific test item | ASO MVP TEST - example | Phase validation | DEV |  | Synthetic/demo only | Yes | Not Started | Do not use real customer data

## Journey Register
Phase 3 — Journey Register
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Journey | Entry type | Audience | Compliance profile | Status | Trigger/segment | Writeback fields | Notes
JRNY - ASO - Lead Nurture - v1 | Segment or trigger | Lead | Global Commercial | Not Started | Lead - Nurture Ready / ASO Lead Nurture Requested | Communication State; Journey Status; Last Interaction
JRNY - ASO - Qualified Lead Follow Up - v1 | Segment or trigger | Lead/Contact | Global Commercial | Not Started | ASO Qualified Lead Follow Up Requested | Journey ledger
JRNY - ASO - Opportunity Progression - v1 | Trigger | Contact | Global Commercial | Not Started | ASO Opportunity Progression Requested | Journey ledger

## Email Asset Register
Phase 3 — Email Asset Register
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Email asset | Journey | Compliance profile | Topic | Personalization fields | Approval status | Test send result | Notes
EML - Lead Nurture - Initial | Lead Nurture | Global Commercial | Lead | Approved Dataverse fields only | Not Started
EML - Qualified Lead - Follow Up | Qualified Lead Follow Up | Global Commercial | Qualified Lead | Approved Dataverse fields only | Not Started

## Consent Matrix
Phase 3 — Consent Matrix
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Consent source | Normalized field | Allowed value | Communication State effect | Hold reason | Owner | Notes
Customer Insights consent | aso_emailconsentstatus | OptedIn | Eligible if other criteria pass |  | CI Operator
Customer Insights consent | aso_emailconsentstatus | OptedOut/Blocked | Suppressed or Blocked | Consent withdrawn or blocked | CI Operator

## Source References
Phase 3 Source References
Source files and guide sections used to populate this workbook.
Source | Relevant section / use | Notes
MAIN_Agentic Sales Orchestrator - Build Guide.md | Delivery phases, target architecture, product boundaries, naming standards, phase runbook content | Primary enterprise guide for all phases
ASO_Phase2_Dataverse_Schema_Sales_Form_MVP_Guidance.md | Phase 2 MVP guidance, data dictionary/security/gap tracking and Dataverse schema runbook | Primary detailed guide for Phase 2 workbook
Pasted text.txt | MVP adaptation rules, answer structure, documentation expectations, architecture boundary rules | Used to align workbook controls and phase-gate style
D365_Success_by_Design.docx | General delivery assurance context | Referenced as general programme quality context where relevant