## Dashboard
ASO Phase 4 Workbook — SAP Integration Through Azure Functions and APIM
Customer-ready enterprise/MVP tracking workbook for Agentic Sales Orchestrator.
Current phase | Phase 4 | Phase Control Dashboard
Objective | Create the governed SAP integration boundary through Azure Functions and API Management with no direct SAP access from agents or flows. | Total tasks | 15
Primary solution/component | Azure resources / ASO.Automation / ASO.Core | Done | 0
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — Phase 4 / SAP integration sections | In progress | 0
Enterprise target | SAP communication arrangements, endpoint inventory, Azure Function wrapper, APIM policies, Key Vault secrets, App Insights telemetry, correlation headers, retries and idempotency. | Blocked | 0
MVP/trial adaptation | If SAP/APIM/Functions are unavailable, create mock endpoints and interface contracts, keep feature flag ERP submit off, and document production gaps. | Completion % | 0%
Non-negotiable | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Open risks/issues | 3
|  | Open production gaps | 3
|  | Validation passed | 0
|  | Phase Gate Criteria | Status | Evidence / notes
|  | Prerequisites confirmed | Not Started
|  | Build tracker complete or deferred with approval | Not Started
|  | Validation checklist passed | Not Started
|  | Risks/issues assessed | Not Started
|  | Production gaps logged | Not Started
|  | Solution/export evidence recorded | Not Started
|  | Architecture boundaries preserved | Not Started

## Phase Charter
Phase 4 Charter
Scope, assumptions, boundaries, and operating model for this phase.
Field | Value
Phase | Phase 4 — SAP Integration Through Azure Functions and APIM
Objective | Create the governed SAP integration boundary through Azure Functions and API Management with no direct SAP access from agents or flows.
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — Phase 4 / SAP integration sections
Primary solution/component | Azure resources / ASO.Automation / ASO.Core
Enterprise target | SAP communication arrangements, endpoint inventory, Azure Function wrapper, APIM policies, Key Vault secrets, App Insights telemetry, correlation headers, retries and idempotency.
MVP/trial-friendly implementation | If SAP/APIM/Functions are unavailable, create mock endpoints and interface contracts, keep feature flag ERP submit off, and document production gaps.
What to simulate if blocked | Use mocks/placeholders/manual validation only where product trial or licensing limits block the real enterprise component. Record every shortcut as MVP-only.
What to skip for now | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate.
Architecture boundary | Dataverse is operational truth; Customer Insights handles outbound lifecycle communications; Power Automate executes deterministically; Foundry orchestrates; SAP only through APIM + Azure Functions; HubSpot is ingress only and last.

## Build Tracker
Phase 4 Build Tracker
Track every build/configuration item through owner, status, evidence and validation.
ID | Work item | Stream | Implementation instruction | Expected outcome | Owner role | Status | Priority | Start date | Target date | Completed date | Evidence / link | Validation result | Notes
4.1 | Prepare SAP communication users | SAP | Read-only and write-capable users for approved submissions only | Users created or SAP gap logged | SAP Admin | Not Started | High
4.2 | Create SAP communication system/arrangements | SAP | Required APIs and arrangements | Arrangement inventory completed | SAP Admin | Not Started | High
4.3 | Create SAP endpoint inventory | Design | Business partner, customer profile, products, sales orders, commercial submit | Inventory completed | Integration Architect | Not Started | High
4.4 | Create Azure resource group | Azure | rg-aso-dev-weu | Resource group exists or MVP gap logged | Azure Admin | Not Started | Medium
4.5 | Create Storage, App Insights, Key Vault | Azure | stasoDEV001, appi-aso-dev-weu, kv-aso-dev-weu | Resources created | Azure Admin | Not Started | Medium
4.6 | Create Function App | Azure | func-aso-sap-dev-weu with managed identity | Function App exists | Developer | Not Started | High
4.7 | Grant Key Vault access | Security | Function App MI can read secrets | Access validated | Azure Admin | Not Started | High
4.8 | Configure Function App settings | Configuration | SAP_BASE_URL, auth mode, secret names, timeout/retry, App Insights, audience | Settings recorded | Developer | Not Started | High
4.9 | Implement wrapper read endpoints | Development | business-partner search, profile, products, orders, commercial profile | Endpoints tested | Developer | Not Started | High
4.10 | Implement commercial prepare/submit endpoints | Development | Prepare order and submit order with idempotency | Endpoints tested in mock/SAP | Developer | Not Started | High
4.11 | Create APIM | Azure | apim-aso-dev-weu | APIM exists | Azure Admin | Not Started | High
4.12 | Import Function API into APIM | APIM | Path /aso/sap/v1 | API published | Integration Developer | Not Started | High
4.13 | Configure APIM policies | APIM | Validate JWT, require x-correlation-id and x-message-id, rate limit, backend, trace | Policies deployed | Integration Developer | Not Started | High
4.14 | Validate response contract | Testing | message_id, correlation_id, status, data, error, trace_id | Contract tests pass | Tester | Not Started | High
4.15 | Phase gate: SAP boundary validated | Gate | No direct SAP access outside APIM/Functions | Gate signed off | Solution Architect | Not Started | High

## Runbook
Phase 4 Click-by-Click Runbook
Operational build notes for step-by-step execution. Keep evidence and blockers current.
Step | Click path / action | Exact name or value | Configuration notes | Expected UI result | Common mistake to avoid | Status | Evidence
4.1 | Read-only and write-capable users for approved submissions only |  | Users created or SAP gap logged | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.2 | Required APIs and arrangements |  | Arrangement inventory completed | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.3 | Business partner, customer profile, products, sales orders, commercial submit |  | Inventory completed | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.4 | rg-aso-dev-weu |  | Resource group exists or MVP gap logged | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.5 | stasoDEV001, appi-aso-dev-weu, kv-aso-dev-weu |  | Resources created | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.6 | func-aso-sap-dev-weu with managed identity |  | Function App exists | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.7 | Function App MI can read secrets |  | Access validated | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.8 | SAP_BASE_URL, auth mode, secret names, timeout/retry, App Insights, audience |  | Settings recorded | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.9 | business-partner search, profile, products, orders, commercial profile |  | Endpoints tested | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.10 | Prepare order and submit order with idempotency |  | Endpoints tested in mock/SAP | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.11 | apim-aso-dev-weu |  | APIM exists | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.12 | Path /aso/sap/v1 |  | API published | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.13 | Validate JWT, require x-correlation-id and x-message-id, rate limit, backend, trace |  | Policies deployed | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.14 | message_id, correlation_id, status, data, error, trace_id |  | Contract tests pass | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started
4.15 | No direct SAP access outside APIM/Functions |  | Gate signed off | Visible/configured in the correct solution/component | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Not Started

## Config Register
Phase 4 Configuration Register
Names, values, IDs, owners and environment-specific configuration.
Type | Name / schema | Purpose / value | Required level | MVP note | Owner | Status | Environment | Actual value / ID | Evidence / link
Azure Resource Group | rg-aso-dev-weu | DEV resource group | Recommended | Use region-residency-compliant suffix |  | Not Started | DEV
Function App | func-aso-sap-dev-weu | SAP wrapper app | Required in enterprise | MVP may mock |  | Not Started | DEV
APIM | apim-aso-dev-weu | SAP API gateway | Required in enterprise | MVP may mock/document |  | Not Started | DEV
Key Vault | kv-aso-dev-weu | Secret storage | Required | No secrets in workbook |  | Not Started | DEV
App Insights | appi-aso-dev-weu | Telemetry | Required | Log correlation IDs |  | Not Started | DEV
API Path | /aso/sap/v1 | APIM base path | Required | Versioned API |  | Not Started | DEV

## Validation Checklist
Phase 4 Validation Checklist
Gate checks that must pass before the next major phase.
ID | Validation item | Expected evidence | Owner | Criticality | Passed? | Evidence / link | Notes
VAL-4.1 | SAP endpoint inventory is completed | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-4.2 | No direct SAP connection exists from agents, Dataverse, or flows | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-4.3 | Function wrapper responses include message_id, correlation_id, status, data, error, trace_id | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-4.4 | APIM policies require correlation headers and validated auth | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-4.5 | ERP submit feature flag remains off until approval and full validation | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-4.6 | Secrets are stored in Key Vault, not in workbooks or code | Screenshot, record URL, export file, test result, or decision log entry |  | High | No

## Decision Log
Phase 4 Decision Log
Architecture, MVP shortcut, security, ALM, data, integration and product decisions.
Decision ID | Date | Decision area | Decision | Options considered | Rationale | Owner | Status | Impacted phase/component | Follow-up action
DEC-4.001 | 46161 | Scope | Use this workbook as the control file for Phase 4. | Use ad hoc notes; use one master tracker; use phase workbook | Separate phase workbook gives clear gate control and upgrade path. | Solution Architect | Approved | Phase 4
DEC-4.002 | 46161 | MVP adaptation | All demo shortcuts must be recorded in Production Gap Log. | Ignore shortcuts; document later; record immediately | Prevents MVP shortcuts becoming hidden production risks. | Project Manager | Approved | Phase 4

## Risk & Issue Log
Phase 4 Risk & Issue Log
Track delivery risks, blockers, mitigations, and resolution evidence.
ID | Type | Area | Risk / issue | Impact | Probability | Mitigation / action | Status | Owner | Due date | Evidence / notes
RISK-4.001 | Risk | MVP constraints | Trial/free-tier limitations may block enterprise components. | May require mocks/manual validation | Medium | Document blocker and production gap; preserve target architecture boundary. | Open
RISK-4.002 | Risk | ALM | Single DEV environment can hide promotion issues. | Production upgrade risk | Medium | Export solution backups; document future environment runway. | Open
RISK-4.003 | Risk | Architecture boundary | Do not connect directly to SAP from Dataverse, Foundry, Sales agents, or Power Automate. | Supportability and governance risk | Low | Use validation checklist and phase gate before progressing. | Open

## Production Gap Log
Phase 4 Production Gap Log
Every MVP simplification must have a production risk and upgrade path.
Area | MVP decision | Production gap | Risk / limitation | Future production action | Owner | Status | Target phase/date | Decision reference
SAP access | Use mock endpoints if SAP unavailable | No live SAP validation | MVP-only limitation; assess before production | Replace mocks with SAP arrangements before integration testing |  | Open
APIM | Document API contract if APIM unavailable | No real policy enforcement | MVP-only limitation; assess before production | Deploy APIM before production |  | Open
Secrets | No secrets stored in workbook | Credentials not configured in MVP | MVP-only limitation; assess before production | Use Key Vault and managed identities |  | Open

## Security & Controls
Phase 4 Security & Controls
Security, compliance, data, integration, AI and ALM control checks.
Control area | Control requirement | Applies in this phase? | MVP implementation | Production expectation | Owner | Status | Evidence / notes
ALM | All changes are solution-aware; no default solution build | Yes | Use named ASO solution(s) | Managed solution promotion with pipeline |  | Not Started
Security | Least privilege and admin access restrictions | Yes | Document roles; limit admin access | RBAC/FLS fully enforced |  | Not Started
Data integrity | External IDs, keys, dedupe where applicable | Conditional | Create or document controls | Automated enforcement |  | Not Started
AI governance | AI output advisory until validated by governed orchestration | Conditional | Use review fields and decision log | Foundry policy/evals |  | Not Started
Communication governance | Customer Insights is the only lifecycle outbound channel | Conditional | Do not send outside CIJ | Compliance profile, consent, audit |  | Not Started
SAP boundary | SAP only through APIM + Azure Functions | Conditional | Mock or contract-only where unavailable | APIM/JWT/idempotency/telemetry |  | Not Started
Secrets | No secrets in workbook, flows, code or prompts | Yes | Use placeholders | Key Vault and managed identity |  | Not Started
Observability | Correlation IDs and run logging | Conditional | Use logs/registers | App Insights + Dataverse dashboards |  | Not Started

## ALM & Release
Phase 4 ALM & Release Register
Track solution exports, versioning, deployment evidence and rollback notes.
ID | Solution/component | Version | Change summary | Export/deploy type | Environment | Date | Owner | File/link | Validation status | Rollback notes
ALM-4.001 | Azure resources / ASO.Automation / ASO.Core | 0.1.0 | Initial Phase 4 setup | Manual export backup | DEV |  |  |  | Not Started

## Test Data
Phase 4 Test Data Register
Synthetic records and test users used during MVP/demo validation.
ID | Record type | Record name | Purpose | Created in environment | Owner | Data classification | Cleanup needed? | Status | Notes
TD-4.001 | Lead/Opportunity/Account/Contact or component-specific test item | ASO MVP TEST - example | Phase validation | DEV |  | Synthetic/demo only | Yes | Not Started | Do not use real customer data

## API Contract Register
Phase 4 — API Contract Register
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Endpoint | Method | Purpose | Read/write | Auth | Required headers | Response contract | Status | Notes
/sap/business-partner/search | GET | Business partner search | Read | APIM JWT | x-correlation-id; x-message-id | message_id/correlation_id/status/data/error/trace_id | Not Started
/sap/commercial/submit-order | POST | Submit order after approval | Write | APIM JWT | x-correlation-id; x-message-id; idempotency-key | same | Not Started | No blind retries

## Endpoint Inventory
Phase 4 — Endpoint Inventory
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Capability | Endpoint | Method | Used by | Read/write | Auth | Status | Notes
Business partner search | /business-partner/search | GET | Foundry/lead agents via wrapper | Read | APIM→Function→SAP | Not Started | No direct agent access
Submit order | /commercial/submit-order | POST | Power Automate after approval | Write | APIM | Not Started | Idempotency required

## Integration Test Matrix
Phase 4 — Integration Test Matrix
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Test ID | Scenario | Endpoint/component | Expected result | Status | Evidence | Notes
IT-4.001 | SAP wrapper returns success contract | Function/APIM | Valid standard response | Not Started
IT-4.002 | SAP timeout handled | Function/APIM | Retry/failed response logged | Not Started

## Source References
Phase 4 Source References
Source files and guide sections used to populate this workbook.
Source | Relevant section / use | Notes
MAIN_Agentic Sales Orchestrator - Build Guide.md | Delivery phases, target architecture, product boundaries, naming standards, phase runbook content | Primary enterprise guide for all phases
ASO_Phase2_Dataverse_Schema_Sales_Form_MVP_Guidance.md | Phase 2 MVP guidance, data dictionary/security/gap tracking and Dataverse schema runbook | Primary detailed guide for Phase 2 workbook
Pasted text.txt | MVP adaptation rules, answer structure, documentation expectations, architecture boundary rules | Used to align workbook controls and phase-gate style
D365_Success_by_Design.docx | General delivery assurance context | Referenced as general programme quality context where relevant