## Dashboard
ASO Phase 7 Workbook — Power Automate Deterministic Flows
Customer-ready enterprise/MVP tracking workbook for Agentic Sales Orchestrator.
Current phase | Phase 7 | Phase Control Dashboard
Objective | Create solution-aware deterministic flows that invoke Foundry, update Dataverse, handle approvals, synchronize Customer Insights state, and log errors. | Total tasks | 15
Primary solution/component | ASO.Automation | Done | 0
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — Phase 7 / Power Automate sections | In progress | 0
Enterprise target | Solution-aware cloud flows with connection references, environment variables, trigger conditions, concurrency, structured scopes, retries, correlation IDs, and logging. | Blocked | 0
MVP/trial adaptation | If Foundry/APIM/CIJ are unavailable, wire flows to mock endpoints or manual placeholders, but preserve scopes, env vars, logging and production-gap entries. | Completion % | 0%
Non-negotiable | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Open risks/issues | 3
|  | Open production gaps | 3
|  | Validation passed | 0
|  | Phase Gate Criteria | Status | Evidence / notes
|  | Prerequisites confirmed | Not Started
|  | Build tracker complete or deferred with approval | Not Started
|  | Validation checklist passed | Not Started
|  | Risks/issues assessed | Not Started
|  | Production gaps logged | Not Started
|  | Solution/export evidence recorded | Not Started
|  | Architecture boundaries preserved | Not Started

## Phase Charter
Phase 7 Charter
Scope, assumptions, boundaries, and operating model for this phase.
Field | Value
Phase | Phase 7 — Power Automate Deterministic Flows
Objective | Create solution-aware deterministic flows that invoke Foundry, update Dataverse, handle approvals, synchronize Customer Insights state, and log errors.
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — Phase 7 / Power Automate sections
Primary solution/component | ASO.Automation
Enterprise target | Solution-aware cloud flows with connection references, environment variables, trigger conditions, concurrency, structured scopes, retries, correlation IDs, and logging.
MVP/trial-friendly implementation | If Foundry/APIM/CIJ are unavailable, wire flows to mock endpoints or manual placeholders, but preserve scopes, env vars, logging and production-gap entries.
What to simulate if blocked | Use mocks/placeholders/manual validation only where product trial or licensing limits block the real enterprise component. Record every shortcut as MVP-only.
What to skip for now | Power Automate must not perform AI reasoning or send customer lifecycle emails.
Architecture boundary | Dataverse is operational truth; Customer Insights handles outbound lifecycle communications; Power Automate executes deterministically; Foundry orchestrates; SAP only through APIM + Azure Functions; HubSpot is ingress only and last.

## Build Tracker
Phase 7 Build Tracker
Track every build/configuration item through owner, status, evidence and validation.
ID | Work item | Stream | Implementation instruction | Expected outcome | Owner role | Status | Priority | Start date | Target date | Completed date | Evidence / link | Validation result | Notes
7.1 | Confirm ASO.Automation prerequisites | Prerequisite | Connection references and environment variables exist | Prereqs confirmed | Maker/Admin | Not Started | High
7.2 | Define common flow standards | Design | Scopes, correlation IDs, retry policy, trigger conditions, logging | Standards recorded | Solution Architect | Not Started | High
7.3 | Create Lead Dispatch to Foundry flow | Flow A | ASO - Lead - Dispatch to Foundry | Flow created in solution | Maker | Not Started | High
7.4 | Configure Lead trigger filtering | Flow A | Select columns and loop prevention | Trigger conditions validated | Maker | Not Started | High
7.5 | Build Lead payload and status updates | Flow A | Set Running, correlation ID, canonical payload | Payload validated | Maker | Not Started | High
7.6 | Process Lead Foundry response | Flow A | Update AI, Foundry, communication fields and Agent Run Log | Response mapping tested | Maker | Not Started | High
7.7 | Create Opportunity Dispatch to Foundry flow | Flow B | ASO - Opportunity - Dispatch to Foundry | Flow created in solution | Maker | Not Started | High
7.8 | Create CIJ Participation Sync flow | Flow C | ASO - CIJ - Participation Sync | Flow created or CIJ gap logged | Maker | Not Started | Medium
7.9 | Create Consent Normalization flow | Flow D | ASO - CIJ - Consent Sync | Flow created or trigger gap logged | Maker | Not Started | Medium
7.10 | Create Commercial Approval and SAP Submit flow | Flow E | ASO - Commercial - Approval and SAP Submit | Flow created with ERP submit disabled until ready | Maker | Not Started | High
7.11 | Create Replay Failed Run flow | Flow F | ASO - Operations - Replay Failed Run | Flow created | Maker | Not Started | Medium
7.12 | Add error handling and Agent Run Log writes | Reliability | Try/catch scopes, failed log rows, task/alert creation | Error handling tested | Maker | Not Started | High
7.13 | Test trigger loop prevention | Testing | Ensure updates do not recursively re-trigger | No loop observed | Tester | Not Started | High
7.14 | Export ASO.Automation backup | ALM | Manual solution export | Backup recorded | Maker/Admin | Not Started | Medium
7.15 | Phase gate: deterministic execution validated | Gate | Flows execute deterministic updates only | Gate signed off | Solution Architect | Not Started | High

## Runbook
Phase 7 Click-by-Click Runbook
Operational build notes for step-by-step execution. Keep evidence and blockers current.
Step | Click path / action | Exact name or value | Configuration notes | Expected UI result | Common mistake to avoid | Status | Evidence
7.1 | Connection references and environment variables exist |  | Prereqs confirmed | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.2 | Scopes, correlation IDs, retry policy, trigger conditions, logging |  | Standards recorded | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.3 | ASO - Lead - Dispatch to Foundry |  | Flow created in solution | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.4 | Select columns and loop prevention |  | Trigger conditions validated | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.5 | Set Running, correlation ID, canonical payload |  | Payload validated | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.6 | Update AI, Foundry, communication fields and Agent Run Log |  | Response mapping tested | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.7 | ASO - Opportunity - Dispatch to Foundry |  | Flow created in solution | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.8 | ASO - CIJ - Participation Sync |  | Flow created or CIJ gap logged | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.9 | ASO - CIJ - Consent Sync |  | Flow created or trigger gap logged | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.10 | ASO - Commercial - Approval and SAP Submit |  | Flow created with ERP submit disabled until ready | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.11 | ASO - Operations - Replay Failed Run |  | Flow created | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.12 | Try/catch scopes, failed log rows, task/alert creation |  | Error handling tested | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.13 | Ensure updates do not recursively re-trigger |  | No loop observed | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.14 | Manual solution export |  | Backup recorded | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started
7.15 | Flows execute deterministic updates only |  | Gate signed off | Visible/configured in the correct solution/component | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Not Started

## Config Register
Phase 7 Configuration Register
Names, values, IDs, owners and environment-specific configuration.
Type | Name / schema | Purpose / value | Required level | MVP note | Owner | Status | Environment | Actual value / ID | Evidence / link
Flow | ASO - Lead - Dispatch to Foundry | Lead event to Foundry | Required | Solution-aware |  | Not Started | DEV
Flow | ASO - Opportunity - Dispatch to Foundry | Opportunity event to Foundry | Required | Solution-aware |  | Not Started | DEV
Flow | ASO - CIJ - Participation Sync | Journey writeback sync | Recommended | Depends on CIJ |  | Not Started | DEV
Flow | ASO - CIJ - Consent Sync | Consent normalization | Recommended | Depends on CIJ |  | Not Started | DEV
Flow | ASO - Commercial - Approval and SAP Submit | Approval-gated SAP submit | Required | Do not enable writes until Phase 4 tested |  | Not Started | DEV
Flow | ASO - Operations - Replay Failed Run | Controlled replay | Recommended | AI Operations Reviewer role |  | Not Started | DEV

## Validation Checklist
Phase 7 Validation Checklist
Gate checks that must pass before the next major phase.
ID | Validation item | Expected evidence | Owner | Criticality | Passed? | Evidence / link | Notes
VAL-7.1 | All flows are solution-aware in ASO.Automation | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-7.2 | No flow has hardcoded URLs; environment variables are used | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-7.3 | Connection references are used instead of personal production connections | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-7.4 | Every run uses message_id and correlation_id | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-7.5 | External calls pass correlation headers | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-7.6 | Error handling scopes write to Agent Run Log | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-7.7 | No customer lifecycle email is sent by Power Automate | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-7.8 | ERP submit path requires human approval and idempotency | Screenshot, record URL, export file, test result, or decision log entry |  | High | No

## Decision Log
Phase 7 Decision Log
Architecture, MVP shortcut, security, ALM, data, integration and product decisions.
Decision ID | Date | Decision area | Decision | Options considered | Rationale | Owner | Status | Impacted phase/component | Follow-up action
DEC-7.001 | 46161 | Scope | Use this workbook as the control file for Phase 7. | Use ad hoc notes; use one master tracker; use phase workbook | Separate phase workbook gives clear gate control and upgrade path. | Solution Architect | Approved | Phase 7
DEC-7.002 | 46161 | MVP adaptation | All demo shortcuts must be recorded in Production Gap Log. | Ignore shortcuts; document later; record immediately | Prevents MVP shortcuts becoming hidden production risks. | Project Manager | Approved | Phase 7

## Risk & Issue Log
Phase 7 Risk & Issue Log
Track delivery risks, blockers, mitigations, and resolution evidence.
ID | Type | Area | Risk / issue | Impact | Probability | Mitigation / action | Status | Owner | Due date | Evidence / notes
RISK-7.001 | Risk | MVP constraints | Trial/free-tier limitations may block enterprise components. | May require mocks/manual validation | Medium | Document blocker and production gap; preserve target architecture boundary. | Open
RISK-7.002 | Risk | ALM | Single DEV environment can hide promotion issues. | Production upgrade risk | Medium | Export solution backups; document future environment runway. | Open
RISK-7.003 | Risk | Architecture boundary | Power Automate must not perform AI reasoning or send customer lifecycle emails. | Supportability and governance risk | Low | Use validation checklist and phase gate before progressing. | Open

## Production Gap Log
Phase 7 Production Gap Log
Every MVP simplification must have a production risk and upgrade path.
Area | MVP decision | Production gap | Risk / limitation | Future production action | Owner | Status | Target phase/date | Decision reference
Foundry endpoint | Use mock if Foundry unavailable | No live AI orchestration | MVP-only limitation; assess before production | Connect real Foundry endpoint in Phase 6/7 integration |  | Open
CIJ triggers | Use scheduled/manual sync if triggers unavailable | Lower immediacy | MVP-only limitation; assess before production | Use native writeback/triggers in production |  | Open
Commercial submit | Keep feature flag off | No live SAP order submit | MVP-only limitation; assess before production | Enable after Phase 4 and UAT approval |  | Open

## Security & Controls
Phase 7 Security & Controls
Security, compliance, data, integration, AI and ALM control checks.
Control area | Control requirement | Applies in this phase? | MVP implementation | Production expectation | Owner | Status | Evidence / notes
ALM | All changes are solution-aware; no default solution build | Yes | Use named ASO solution(s) | Managed solution promotion with pipeline |  | Not Started
Security | Least privilege and admin access restrictions | Yes | Document roles; limit admin access | RBAC/FLS fully enforced |  | Not Started
Data integrity | External IDs, keys, dedupe where applicable | Conditional | Create or document controls | Automated enforcement |  | Not Started
AI governance | AI output advisory until validated by governed orchestration | Conditional | Use review fields and decision log | Foundry policy/evals |  | Not Started
Communication governance | Customer Insights is the only lifecycle outbound channel | Conditional | Do not send outside CIJ | Compliance profile, consent, audit |  | Not Started
SAP boundary | SAP only through APIM + Azure Functions | Conditional | Mock or contract-only where unavailable | APIM/JWT/idempotency/telemetry |  | Not Started
Secrets | No secrets in workbook, flows, code or prompts | Yes | Use placeholders | Key Vault and managed identity |  | Not Started
Observability | Correlation IDs and run logging | Conditional | Use logs/registers | App Insights + Dataverse dashboards |  | Not Started

## ALM & Release
Phase 7 ALM & Release Register
Track solution exports, versioning, deployment evidence and rollback notes.
ID | Solution/component | Version | Change summary | Export/deploy type | Environment | Date | Owner | File/link | Validation status | Rollback notes
ALM-7.001 | ASO.Automation | 0.1.0 | Initial Phase 7 setup | Manual export backup | DEV |  |  |  | Not Started

## Test Data
Phase 7 Test Data Register
Synthetic records and test users used during MVP/demo validation.
ID | Record type | Record name | Purpose | Created in environment | Owner | Data classification | Cleanup needed? | Status | Notes
TD-7.001 | Lead/Opportunity/Account/Contact or component-specific test item | ASO MVP TEST - example | Phase validation | DEV |  | Synthetic/demo only | Yes | Not Started | Do not use real customer data

## Flow Register
Phase 7 — Flow Register
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Flow name | Trigger | Solution | Connection refs | Env vars | Status | Owner | Notes
ASO - Lead - Dispatch to Foundry | Lead event to Foundry | ASO.Automation | Required | Required | Not Started |  | Solution-aware
ASO - Opportunity - Dispatch to Foundry | Opportunity event to Foundry | ASO.Automation | Required | Required | Not Started |  | Solution-aware
ASO - CIJ - Participation Sync | Journey writeback sync | ASO.Automation | Required | Required | Not Started |  | Depends on CIJ
ASO - CIJ - Consent Sync | Consent normalization | ASO.Automation | Required | Required | Not Started |  | Depends on CIJ
ASO - Commercial - Approval and SAP Submit | Approval-gated SAP submit | ASO.Automation | Required | Required | Not Started |  | Do not enable writes until Phase 4 tested
ASO - Operations - Replay Failed Run | Controlled replay | ASO.Automation | Required | Required | Not Started |  | AI Operations Reviewer role

## Error Handling Matrix
Phase 7 — Error Handling Matrix
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Component | Failure | Detection | Handling action | Log target | Retry policy | Status | Notes
Lead Dispatch | Foundry timeout | HTTP failure | Set status Failed; log error; create ops task | Agent Run Log | Safe retry policy | Not Started
Commercial Submit | SAP timeout | APIM/Function error | Do not blindly resubmit; check idempotency | Pending Commercial Action | Idempotency required | Not Started

## Payload Contract
Phase 7 — Payload Contract
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Flow | Payload field | Source | Required? | Notes
ASO - Lead - Dispatch to Foundry | message_id | guid() | Yes | Per run
ASO - Lead - Dispatch to Foundry | correlation_id | Lead aso_aicorrelationid or guid() | Yes | Preserved across replay

## Source References
Phase 7 Source References
Source files and guide sections used to populate this workbook.
Source | Relevant section / use | Notes
MAIN_Agentic Sales Orchestrator - Build Guide.md | Delivery phases, target architecture, product boundaries, naming standards, phase runbook content | Primary enterprise guide for all phases
ASO_Phase2_Dataverse_Schema_Sales_Form_MVP_Guidance.md | Phase 2 MVP guidance, data dictionary/security/gap tracking and Dataverse schema runbook | Primary detailed guide for Phase 2 workbook
Pasted text.txt | MVP adaptation rules, answer structure, documentation expectations, architecture boundary rules | Used to align workbook controls and phase-gate style
D365_Success_by_Design.docx | General delivery assurance context | Referenced as general programme quality context where relevant