## Dashboard
ASO Phase 9 Workbook — End-to-End Testing Without HubSpot
Customer-ready enterprise/MVP tracking workbook for Agentic Sales Orchestrator.
Current phase | Phase 9 | Phase Control Dashboard
Objective | Validate the full governed process using Dataverse-created or simulated records before enabling HubSpot ingress. | Total tasks | 13
Primary solution/component | All ASO solutions / Sales Hub / CIJ / Foundry / SAP mock or live | Done | 0
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — delivery phase 9 and E2E test scripts | In progress | 0
Enterprise target | Integrated tests prove Lead/Opportunity/CIJ/Foundry/Sales agents/SAP/APIM/Power Automate/observability work together before external ingress is connected. | Blocked | 0
MVP/trial adaptation | Use manually created Dataverse records and mock SAP/Foundry/CIJ outputs where trials block real components, but keep pass criteria and production gaps explicit. | Completion % | 0%
Non-negotiable | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Open risks/issues | 3
|  | Open production gaps | 3
|  | Validation passed | 0
|  | Phase Gate Criteria | Status | Evidence / notes
|  | Prerequisites confirmed | Not Started
|  | Build tracker complete or deferred with approval | Not Started
|  | Validation checklist passed | Not Started
|  | Risks/issues assessed | Not Started
|  | Production gaps logged | Not Started
|  | Solution/export evidence recorded | Not Started
|  | Architecture boundaries preserved | Not Started

## Phase Charter
Phase 9 Charter
Scope, assumptions, boundaries, and operating model for this phase.
Field | Value
Phase | Phase 9 — End-to-End Testing Without HubSpot
Objective | Validate the full governed process using Dataverse-created or simulated records before enabling HubSpot ingress.
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — delivery phase 9 and E2E test scripts
Primary solution/component | All ASO solutions / Sales Hub / CIJ / Foundry / SAP mock or live
Enterprise target | Integrated tests prove Lead/Opportunity/CIJ/Foundry/Sales agents/SAP/APIM/Power Automate/observability work together before external ingress is connected.
MVP/trial-friendly implementation | Use manually created Dataverse records and mock SAP/Foundry/CIJ outputs where trials block real components, but keep pass criteria and production gaps explicit.
What to simulate if blocked | Use mocks/placeholders/manual validation only where product trial or licensing limits block the real enterprise component. Record every shortcut as MVP-only.
What to skip for now | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed.
Architecture boundary | Dataverse is operational truth; Customer Insights handles outbound lifecycle communications; Power Automate executes deterministically; Foundry orchestrates; SAP only through APIM + Azure Functions; HubSpot is ingress only and last.

## Build Tracker
Phase 9 Build Tracker
Track every build/configuration item through owner, status, evidence and validation.
ID | Work item | Stream | Implementation instruction | Expected outcome | Owner role | Status | Priority | Start date | Target date | Completed date | Evidence / link | Validation result | Notes
9.1 | Prepare E2E test data set | Test Prep | Create ASO MVP records in Dataverse; no HubSpot yet | Test data ready | Tester | Not Started | High
9.2 | Test new lead with no SAP match | Test Case | Simulate net-new lead; Foundry/SAP no match; journey eligible | Pass/fail recorded | Tester | Not Started | High
9.3 | Test existing SAP customer lead | Test Case | Simulate SAP match and existing account review | Pass/fail recorded | Tester | Not Started | High
9.4 | Test opportunity risk and deal close guidance | Test Case | Opportunity agent/Foundry risk and next-best-action | Pass/fail recorded | Tester | Not Started | High
9.5 | Test commercial approval and SAP submit | Test Case | Approval-gated Pending Commercial Action and APIM/Function submit or mock | Pass/fail recorded | Tester | Not Started | High
9.6 | Test Sales agent and Foundry disagreement | Safety Test | Foundry requires human review | Pass/fail recorded | Tester | Not Started | High
9.7 | Test consent block | Safety Test | Opted out/suppressed records must not enter send journey | Pass/fail recorded | Tester | Not Started | High
9.8 | Test schema failure handling | Resilience Test | Invalid Foundry output writes failed Agent Run Log and blocks partial update | Pass/fail recorded | Tester | Not Started | High
9.9 | Test SAP timeout/retry/idempotency | Resilience Test | Safe retry/read behavior and no blind create retry | Pass/fail recorded | Tester | Not Started | High
9.10 | Test CIJ journey failure/replay guard | Resilience Test | No duplicate journey entry before ledger review | Pass/fail recorded | Tester | Not Started | Medium
9.11 | Validate dashboards and alerts during tests | Operations | Failures appear in dashboards/runbooks | Operational evidence captured | Ops Lead | Not Started | Medium
9.12 | Create defect log and remediation plan | Defects | Log issues, owner, priority, fix phase | Defect log completed | Project Manager | Not Started | High
9.13 | Phase gate: HubSpot readiness | Gate | E2E test passed without HubSpot | Gate signed off | Solution Architect | Not Started | High

## Runbook
Phase 9 Click-by-Click Runbook
Operational build notes for step-by-step execution. Keep evidence and blockers current.
Step | Click path / action | Exact name or value | Configuration notes | Expected UI result | Common mistake to avoid | Status | Evidence
9.1 | Create ASO MVP records in Dataverse; no HubSpot yet |  | Test data ready | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.2 | Simulate net-new lead; Foundry/SAP no match; journey eligible |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.3 | Simulate SAP match and existing account review |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.4 | Opportunity agent/Foundry risk and next-best-action |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.5 | Approval-gated Pending Commercial Action and APIM/Function submit or mock |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.6 | Foundry requires human review |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.7 | Opted out/suppressed records must not enter send journey |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.8 | Invalid Foundry output writes failed Agent Run Log and blocks partial update |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.9 | Safe retry/read behavior and no blind create retry |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.10 | No duplicate journey entry before ledger review |  | Pass/fail recorded | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.11 | Failures appear in dashboards/runbooks |  | Operational evidence captured | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.12 | Log issues, owner, priority, fix phase |  | Defect log completed | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started
9.13 | E2E test passed without HubSpot |  | Gate signed off | Visible/configured in the correct solution/component | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Not Started

## Config Register
Phase 9 Configuration Register
Names, values, IDs, owners and environment-specific configuration.
Type | Name / schema | Purpose / value | Required level | MVP note | Owner | Status | Environment | Actual value / ID | Evidence / link
Test Record Prefix | ASO MVP TEST - | Identifies synthetic records | Required | Avoid production-looking data |  | Not Started | DEV
Test Suite | E2E without HubSpot | Pre-ingress integrated validation | Required | Must pass before Phase 10 |  | Not Started | DEV
Pass Criteria | No direct SAP/communication violations | Architecture boundary validation | Required | Record evidence |  | Not Started | DEV

## Validation Checklist
Phase 9 Validation Checklist
Gate checks that must pass before the next major phase.
ID | Validation item | Expected evidence | Owner | Criticality | Passed? | Evidence / link | Notes
VAL-9.1 | All test records are clearly marked ASO MVP TEST | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-9.2 | Lead, opportunity, approval, journey, SAP and failure scenarios are tested | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-9.3 | Agent Run Log and dashboards show traces | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-9.4 | Human review is required where safety policy says so | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-9.5 | No HubSpot integration has been enabled | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-9.6 | Defects are tracked and remediated or accepted with signoff | Screenshot, record URL, export file, test result, or decision log entry |  | High | No

## Decision Log
Phase 9 Decision Log
Architecture, MVP shortcut, security, ALM, data, integration and product decisions.
Decision ID | Date | Decision area | Decision | Options considered | Rationale | Owner | Status | Impacted phase/component | Follow-up action
DEC-9.001 | 46161 | Scope | Use this workbook as the control file for Phase 9. | Use ad hoc notes; use one master tracker; use phase workbook | Separate phase workbook gives clear gate control and upgrade path. | Solution Architect | Approved | Phase 9
DEC-9.002 | 46161 | MVP adaptation | All demo shortcuts must be recorded in Production Gap Log. | Ignore shortcuts; document later; record immediately | Prevents MVP shortcuts becoming hidden production risks. | Project Manager | Approved | Phase 9

## Risk & Issue Log
Phase 9 Risk & Issue Log
Track delivery risks, blockers, mitigations, and resolution evidence.
ID | Type | Area | Risk / issue | Impact | Probability | Mitigation / action | Status | Owner | Due date | Evidence / notes
RISK-9.001 | Risk | MVP constraints | Trial/free-tier limitations may block enterprise components. | May require mocks/manual validation | Medium | Document blocker and production gap; preserve target architecture boundary. | Open
RISK-9.002 | Risk | ALM | Single DEV environment can hide promotion issues. | Production upgrade risk | Medium | Export solution backups; document future environment runway. | Open
RISK-9.003 | Risk | Architecture boundary | Do not start HubSpot ingress before end-to-end validation without HubSpot is passed. | Supportability and governance risk | Low | Use validation checklist and phase gate before progressing. | Open

## Production Gap Log
Phase 9 Production Gap Log
Every MVP simplification must have a production risk and upgrade path.
Area | MVP decision | Production gap | Risk / limitation | Future production action | Owner | Status | Target phase/date | Decision reference
Live SAP | Use mock if unavailable | Cannot validate real SAP behavior | MVP-only limitation; assess before production | Run production-like SAP integration test before UAT |  | Open
Live Foundry | Use mock if unavailable | Cannot validate model/orchestration quality | MVP-only limitation; assess before production | Run Foundry evaluation suite |  | Open
CIJ send | Use test mode/no-send if needed | No deliverability proof | MVP-only limitation; assess before production | Run compliance and deliverability testing |  | Open

## Security & Controls
Phase 9 Security & Controls
Security, compliance, data, integration, AI and ALM control checks.
Control area | Control requirement | Applies in this phase? | MVP implementation | Production expectation | Owner | Status | Evidence / notes
ALM | All changes are solution-aware; no default solution build | Yes | Use named ASO solution(s) | Managed solution promotion with pipeline |  | Not Started
Security | Least privilege and admin access restrictions | Yes | Document roles; limit admin access | RBAC/FLS fully enforced |  | Not Started
Data integrity | External IDs, keys, dedupe where applicable | Conditional | Create or document controls | Automated enforcement |  | Not Started
AI governance | AI output advisory until validated by governed orchestration | Conditional | Use review fields and decision log | Foundry policy/evals |  | Not Started
Communication governance | Customer Insights is the only lifecycle outbound channel | Conditional | Do not send outside CIJ | Compliance profile, consent, audit |  | Not Started
SAP boundary | SAP only through APIM + Azure Functions | Conditional | Mock or contract-only where unavailable | APIM/JWT/idempotency/telemetry |  | Not Started
Secrets | No secrets in workbook, flows, code or prompts | Yes | Use placeholders | Key Vault and managed identity |  | Not Started
Observability | Correlation IDs and run logging | Conditional | Use logs/registers | App Insights + Dataverse dashboards |  | Not Started

## ALM & Release
Phase 9 ALM & Release Register
Track solution exports, versioning, deployment evidence and rollback notes.
ID | Solution/component | Version | Change summary | Export/deploy type | Environment | Date | Owner | File/link | Validation status | Rollback notes
ALM-9.001 | All ASO solutions / Sales Hub / CIJ / Foundry / SAP mock or live | 0.1.0 | Initial Phase 9 setup | Manual export backup | DEV |  |  |  | Not Started

## Test Data
Phase 9 Test Data Register
Synthetic records and test users used during MVP/demo validation.
ID | Record type | Record name | Purpose | Created in environment | Owner | Data classification | Cleanup needed? | Status | Notes
TD-9.001 | Lead/Opportunity/Account/Contact or component-specific test item | ASO MVP TEST - example | Phase validation | DEV |  | Synthetic/demo only | Yes | Not Started | Do not use real customer data

## E2E Test Scripts
Phase 9 — E2E Test Scripts
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Test ID | Scenario | Preconditions | Steps | Expected result | Status | Evidence | Defect ID
9.1 | Prepare E2E test data set | Previous phases completed or mock documented | Create ASO MVP records in Dataverse; no HubSpot yet | Test data ready | Not Started
9.2 | Test new lead with no SAP match | Previous phases completed or mock documented | Simulate net-new lead; Foundry/SAP no match; journey eligible | Pass/fail recorded | Not Started
9.3 | Test existing SAP customer lead | Previous phases completed or mock documented | Simulate SAP match and existing account review | Pass/fail recorded | Not Started
9.4 | Test opportunity risk and deal close guidance | Previous phases completed or mock documented | Opportunity agent/Foundry risk and next-best-action | Pass/fail recorded | Not Started
9.5 | Test commercial approval and SAP submit | Previous phases completed or mock documented | Approval-gated Pending Commercial Action and APIM/Function submit or mock | Pass/fail recorded | Not Started
9.6 | Test Sales agent and Foundry disagreement | Previous phases completed or mock documented | Foundry requires human review | Pass/fail recorded | Not Started
9.7 | Test consent block | Previous phases completed or mock documented | Opted out/suppressed records must not enter send journey | Pass/fail recorded | Not Started
9.8 | Test schema failure handling | Previous phases completed or mock documented | Invalid Foundry output writes failed Agent Run Log and blocks partial update | Pass/fail recorded | Not Started
9.9 | Test SAP timeout/retry/idempotency | Previous phases completed or mock documented | Safe retry/read behavior and no blind create retry | Pass/fail recorded | Not Started
9.10 | Test CIJ journey failure/replay guard | Previous phases completed or mock documented | No duplicate journey entry before ledger review | Pass/fail recorded | Not Started

## Defect Log
Phase 9 — Defect Log
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Defect ID | Scenario | Description | Severity | Owner | Status | Target fix | Evidence
DEF-9.001 |  |  | Medium |  | Open

## Evidence Register
Phase 9 — Evidence Register
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Evidence ID | Scenario/control | Evidence type | Location/link | Captured by | Date | Notes
EVD-9.001 |  | Screenshot/log/export

## Source References
Phase 9 Source References
Source files and guide sections used to populate this workbook.
Source | Relevant section / use | Notes
MAIN_Agentic Sales Orchestrator - Build Guide.md | Delivery phases, target architecture, product boundaries, naming standards, phase runbook content | Primary enterprise guide for all phases
ASO_Phase2_Dataverse_Schema_Sales_Form_MVP_Guidance.md | Phase 2 MVP guidance, data dictionary/security/gap tracking and Dataverse schema runbook | Primary detailed guide for Phase 2 workbook
Pasted text.txt | MVP adaptation rules, answer structure, documentation expectations, architecture boundary rules | Used to align workbook controls and phase-gate style
D365_Success_by_Design.docx | General delivery assurance context | Referenced as general programme quality context where relevant