## Dashboard
ASO Phase 10 Workbook — HubSpot Ingress Integration Last
Customer-ready enterprise/MVP tracking workbook for Agentic Sales Orchestrator.
Current phase | Phase 10 | Phase Control Dashboard
Objective | Enable HubSpot as source-only lead/contact ingress after Dynamics/Dataverse orchestration has already been validated. | Total tasks | 12
Primary solution/component | HubSpot / Dynamics 365 Sales / ASO.Core / ASO.Automation | Done | 0
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — HubSpot ingress sections | In progress | 0
Enterprise target | HubSpot native integration or governed connector configured for one-way lead/contact ingress, field mapping, inclusion filters, duplicate detection, and no ownership of opportunity progression. | Blocked | 0
MVP/trial adaptation | If HubSpot trial/integration is unavailable, simulate inbound leads by manually creating Dataverse leads with HubSpot fields populated and document the connector gap. | Completion % | 0%
Non-negotiable | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Open risks/issues | 3
|  | Open production gaps | 3
|  | Validation passed | 0
|  | Phase Gate Criteria | Status | Evidence / notes
|  | Prerequisites confirmed | Not Started
|  | Build tracker complete or deferred with approval | Not Started
|  | Validation checklist passed | Not Started
|  | Risks/issues assessed | Not Started
|  | Production gaps logged | Not Started
|  | Solution/export evidence recorded | Not Started
|  | Architecture boundaries preserved | Not Started

## Phase Charter
Phase 10 Charter
Scope, assumptions, boundaries, and operating model for this phase.
Field | Value
Phase | Phase 10 — HubSpot Ingress Integration Last
Objective | Enable HubSpot as source-only lead/contact ingress after Dynamics/Dataverse orchestration has already been validated.
Source of truth | MAIN_Agentic Sales Orchestrator - Build Guide.md — HubSpot ingress sections
Primary solution/component | HubSpot / Dynamics 365 Sales / ASO.Core / ASO.Automation
Enterprise target | HubSpot native integration or governed connector configured for one-way lead/contact ingress, field mapping, inclusion filters, duplicate detection, and no ownership of opportunity progression.
MVP/trial-friendly implementation | If HubSpot trial/integration is unavailable, simulate inbound leads by manually creating Dataverse leads with HubSpot fields populated and document the connector gap.
What to simulate if blocked | Use mocks/placeholders/manual validation only where product trial or licensing limits block the real enterprise component. Record every shortcut as MVP-only.
What to skip for now | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields.
Architecture boundary | Dataverse is operational truth; Customer Insights handles outbound lifecycle communications; Power Automate executes deterministically; Foundry orchestrates; SAP only through APIM + Azure Functions; HubSpot is ingress only and last.

## Build Tracker
Phase 10 Build Tracker
Track every build/configuration item through owner, status, evidence and validation.
ID | Work item | Stream | Implementation instruction | Expected outcome | Owner role | Status | Priority | Start date | Target date | Completed date | Evidence / link | Validation result | Notes
10.1 | Confirm Phase 9 gate passed | Gate | E2E without HubSpot completed | Gate evidence reviewed | Solution Architect | Not Started | High
10.2 | Sign in to HubSpot as admin | HubSpot | Access connected apps/integrations | Access confirmed | HubSpot Admin | Not Started | Medium
10.3 | Install/configure Microsoft Dynamics 365 integration | HubSpot | Connected app setup | Integration installed or gap logged | HubSpot Admin | Not Started | High
10.4 | Configure CRM sync direction | HubSpot | HubSpot → Dynamics Lead for first release | Direction recorded | HubSpot Admin | Not Started | High
10.5 | Map core fields | Mapping | HubSpot contact ID, source, email, phone, company, title | Mapping completed | Integration Admin | Not Started | High
10.6 | Configure inclusion filters | HubSpot | Only pilot eligible records | Filters tested | HubSpot Admin | Not Started | Medium
10.7 | Test with one lead | Testing | Create one HubSpot lead and sync to Dynamics | Test result logged | Tester | Not Started | High
10.8 | Validate duplicate detection | Data Quality | Lead email/company and HubSpot ID | No duplicate created | Tester | Not Started | High
10.9 | Validate Power Automate lead flow | Automation | Lead dispatch runs after sync | Flow run captured | Tester | Not Started | High
10.10 | Confirm HubSpot restrictions | Governance | No opportunity writeback, no lifecycle sends, no seller-owned overwrite | Restrictions signed off | Solution Architect | Not Started | High
10.11 | Record operational monitoring | Operations | Failed syncs, duplicates, retries | Monitoring registered | Ops Lead | Not Started | Medium
10.12 | Phase gate: ingress validated | Gate | HubSpot ingress works and boundaries preserved | Gate signed off | Solution Architect | Not Started | High

## Runbook
Phase 10 Click-by-Click Runbook
Operational build notes for step-by-step execution. Keep evidence and blockers current.
Step | Click path / action | Exact name or value | Configuration notes | Expected UI result | Common mistake to avoid | Status | Evidence
10.1 | E2E without HubSpot completed |  | Gate evidence reviewed | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.2 | Access connected apps/integrations |  | Access confirmed | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.3 | Connected app setup |  | Integration installed or gap logged | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.4 | HubSpot → Dynamics Lead for first release |  | Direction recorded | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.5 | HubSpot contact ID, source, email, phone, company, title |  | Mapping completed | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.6 | Only pilot eligible records |  | Filters tested | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.7 | Create one HubSpot lead and sync to Dynamics |  | Test result logged | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.8 | Lead email/company and HubSpot ID |  | No duplicate created | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.9 | Lead dispatch runs after sync |  | Flow run captured | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.10 | No opportunity writeback, no lifecycle sends, no seller-owned overwrite |  | Restrictions signed off | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.11 | Failed syncs, duplicates, retries |  | Monitoring registered | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started
10.12 | HubSpot ingress works and boundaries preserved |  | Gate signed off | Visible/configured in the correct solution/component | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Not Started

## Config Register
Phase 10 Configuration Register
Names, values, IDs, owners and environment-specific configuration.
Type | Name / schema | Purpose / value | Required level | MVP note | Owner | Status | Environment | Actual value / ID | Evidence / link
Sync Mode | HubSpot → Dynamics Lead | First release direction | Required | Ingress only |  | Not Started | DEV
Field Mapping | HubSpot contact ID → aso_hubspotcontactid | External ingress key | Required | Do not map to seller-owned fields |  | Not Started | DEV
Field Mapping | source → aso_hubspotsource | Source tracking | Required | Governed source value |  | Not Started | DEV
Field Mapping | email → emailaddress1 | Lead email | Required | Used for dedupe |  | Not Started | DEV
Field Mapping | company → companyname | Lead company | Required | Used for dedupe |  | Not Started | DEV

## Validation Checklist
Phase 10 Validation Checklist
Gate checks that must pass before the next major phase.
ID | Validation item | Expected evidence | Owner | Criticality | Passed? | Evidence / link | Notes
VAL-10.1 | E2E without HubSpot passed before integration | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-10.2 | Sync direction is HubSpot to Dynamics Lead | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-10.3 | HubSpot contact ID maps to aso_hubspotcontactid | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-10.4 | Duplicate detection does not create duplicate leads | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-10.5 | Power Automate lead flow runs after sync | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-10.6 | HubSpot does not send lifecycle communications after Dynamics ingress | Screenshot, record URL, export file, test result, or decision log entry |  | High | No
VAL-10.7 | HubSpot does not own opportunity progression or overwrite seller-owned fields | Screenshot, record URL, export file, test result, or decision log entry |  | High | No

## Decision Log
Phase 10 Decision Log
Architecture, MVP shortcut, security, ALM, data, integration and product decisions.
Decision ID | Date | Decision area | Decision | Options considered | Rationale | Owner | Status | Impacted phase/component | Follow-up action
DEC-10.001 | 46161 | Scope | Use this workbook as the control file for Phase 10. | Use ad hoc notes; use one master tracker; use phase workbook | Separate phase workbook gives clear gate control and upgrade path. | Solution Architect | Approved | Phase 10
DEC-10.002 | 46161 | MVP adaptation | All demo shortcuts must be recorded in Production Gap Log. | Ignore shortcuts; document later; record immediately | Prevents MVP shortcuts becoming hidden production risks. | Project Manager | Approved | Phase 10

## Risk & Issue Log
Phase 10 Risk & Issue Log
Track delivery risks, blockers, mitigations, and resolution evidence.
ID | Type | Area | Risk / issue | Impact | Probability | Mitigation / action | Status | Owner | Due date | Evidence / notes
RISK-10.001 | Risk | MVP constraints | Trial/free-tier limitations may block enterprise components. | May require mocks/manual validation | Medium | Document blocker and production gap; preserve target architecture boundary. | Open
RISK-10.002 | Risk | ALM | Single DEV environment can hide promotion issues. | Production upgrade risk | Medium | Export solution backups; document future environment runway. | Open
RISK-10.003 | Risk | Architecture boundary | HubSpot must not own opportunity progression, lifecycle customer communication, or overwrite seller-owned fields. | Supportability and governance risk | Low | Use validation checklist and phase gate before progressing. | Open

## Production Gap Log
Phase 10 Production Gap Log
Every MVP simplification must have a production risk and upgrade path.
Area | MVP decision | Production gap | Risk / limitation | Future production action | Owner | Status | Target phase/date | Decision reference
HubSpot integration | Simulate with Dataverse leads if unavailable | No real ingress validation | MVP-only limitation; assess before production | Configure native integration before UAT |  | Open
Opportunity writeback | Disabled/not configured | No HubSpot pipeline sync | MVP-only limitation; assess before production | Evaluate only if explicitly approved later |  | Open
Duplicate handling | Test pilot volume only | No scaled data quality proof | MVP-only limitation; assess before production | Run migration-scale duplicate test |  | Open

## Security & Controls
Phase 10 Security & Controls
Security, compliance, data, integration, AI and ALM control checks.
Control area | Control requirement | Applies in this phase? | MVP implementation | Production expectation | Owner | Status | Evidence / notes
ALM | All changes are solution-aware; no default solution build | Yes | Use named ASO solution(s) | Managed solution promotion with pipeline |  | Not Started
Security | Least privilege and admin access restrictions | Yes | Document roles; limit admin access | RBAC/FLS fully enforced |  | Not Started
Data integrity | External IDs, keys, dedupe where applicable | Conditional | Create or document controls | Automated enforcement |  | Not Started
AI governance | AI output advisory until validated by governed orchestration | Conditional | Use review fields and decision log | Foundry policy/evals |  | Not Started
Communication governance | Customer Insights is the only lifecycle outbound channel | Conditional | Do not send outside CIJ | Compliance profile, consent, audit |  | Not Started
SAP boundary | SAP only through APIM + Azure Functions | Conditional | Mock or contract-only where unavailable | APIM/JWT/idempotency/telemetry |  | Not Started
Secrets | No secrets in workbook, flows, code or prompts | Yes | Use placeholders | Key Vault and managed identity |  | Not Started
Observability | Correlation IDs and run logging | Conditional | Use logs/registers | App Insights + Dataverse dashboards |  | Not Started

## ALM & Release
Phase 10 ALM & Release Register
Track solution exports, versioning, deployment evidence and rollback notes.
ID | Solution/component | Version | Change summary | Export/deploy type | Environment | Date | Owner | File/link | Validation status | Rollback notes
ALM-10.001 | HubSpot / Dynamics 365 Sales / ASO.Core / ASO.Automation | 0.1.0 | Initial Phase 10 setup | Manual export backup | DEV |  |  |  | Not Started

## Test Data
Phase 10 Test Data Register
Synthetic records and test users used during MVP/demo validation.
ID | Record type | Record name | Purpose | Created in environment | Owner | Data classification | Cleanup needed? | Status | Notes
TD-10.001 | Lead/Opportunity/Account/Contact or component-specific test item | ASO MVP TEST - example | Phase validation | DEV |  | Synthetic/demo only | Yes | Not Started | Do not use real customer data

## Field Mapping
Phase 10 — Field Mapping
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Source field | Target field | Direction | Transform | Required? | Status | Notes
HubSpot contact ID | aso_hubspotcontactid | HubSpot → Dynamics Lead | As-is | Yes | Not Started | External ingress key
source | aso_hubspotsource | HubSpot → Dynamics Lead | As-is/governed | Yes | Not Started
email | emailaddress1 | HubSpot → Dynamics Lead | As-is | Yes | Not Started | Used for duplicate detection

## Sync Test Log
Phase 10 — Sync Test Log
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Test ID | HubSpot record | Dynamics record | Expected result | Actual result | Duplicate? | Status | Evidence
SYNC-10.001 | ASO MVP TEST - HubSpot Lead 001 |  | One Dynamics Lead created |  | No | Not Started

## Restriction Register
Phase 10 — Restriction Register
Phase-specific enterprise register. Add/maintain rows as implementation progresses.
Restriction | Reason | Enforcement approach | Status | Evidence | Notes
No opportunity writeback | HubSpot is ingress only | Do not map opportunities | Not Started
No lifecycle sends from HubSpot | Customer Insights only | Disable/avoid HubSpot marketing automation | Not Started

## Source References
Phase 10 Source References
Source files and guide sections used to populate this workbook.
Source | Relevant section / use | Notes
MAIN_Agentic Sales Orchestrator - Build Guide.md | Delivery phases, target architecture, product boundaries, naming standards, phase runbook content | Primary enterprise guide for all phases
ASO_Phase2_Dataverse_Schema_Sales_Form_MVP_Guidance.md | Phase 2 MVP guidance, data dictionary/security/gap tracking and Dataverse schema runbook | Primary detailed guide for Phase 2 workbook
Pasted text.txt | MVP adaptation rules, answer structure, documentation expectations, architecture boundary rules | Used to align workbook controls and phase-gate style
D365_Success_by_Design.docx | General delivery assurance context | Referenced as general programme quality context where relevant